Proposal for Building

Dynamic Operational Synchronization & Scheduling Platform

For Berau Coal Transshipment Operations

This document is proprietary to Vector Consulting Group. It should not be disclosed/duplicated or revealed to anybody outside of ABL Group without consent of Vector Consulting Group.

Proposal

Created By Vector Consulting Group – 31-05-2026 R1

Contents

- Executive Summary

- Current Operating Realities

- Root Cause Perspective

- Vector Recommendations

- Business Use Case

- Core Scheduling Philosophy

# 1. Executive Summary

ABL and Berau Coal operate in a highly dynamic and deeply interconnected coal transshipment environment involving cargo planning, coal quality and blending requirements, jetty loading operations, tug-and-barge movement, river navigation constraints, tide windows, bridge crossing windows, CTS availability, OGV loading commitments and field-level operational execution.

Managing transshipments planning and manual execution leads to issues like missing out on OGV scheduled dates while having underutilized assets.

ABL is considering an Auto Scheduling Software which can help them to plan their assets for maximum utilization and achieving an very high On Time and In full (OTIF) for the customers of Berau Coal.

ABL has requested Vector to submit a proposal for the same.

# 2. Current Operating Realities

- Planning is highly dynamic and frequently revised monthly, weekly, daily and sometimes intra-day.

- Demand and voyage planning are often created independently from real-time logistics capacity realities.

- Operational decisions depend heavily on manual coordination, spreadsheets, WhatsApp and planner experience.

- Route cycle times vary significantly across jetties, creating uneven effective fleet capacity.

- Tide windows, bridge schedules and navigation constraints continuously impact movement feasibility.

- Asset positions may be visible through AIS/GPS systems, but operational business-state visibility remains limited.

- CTS allocation, tug-barge reassignment and OGV changes create continuous replanning requirements.

- Field teams often make critical decisions without structured simulation-backed support.

- Current KPIs may drive local optimization instead of synchronized end-to-end flow performance.

- Operational disruptions propagate rapidly across the entire chain due to lack of synchronized visibility.

# 3. Root Cause Perspective

- The current challenge is not just a scheduling software problem. Bigger Issue is, Berau Coal generates demand commitments and OGV plan without continuous synchronization with

- Actual WIP,

- Tug-barge loading,

- Route cycle realities,

- Tide windows,

- Bridge constraints,

- CTS capacities,

- Jetty congestion,

- Real operational availability,

- The above resulting in operational mismatch and instability. Operation therefore suffers from

- Reactive planning,

- Excessive waiting,

- Underutilized assets,

- Repeated reassignment

- The fundamental business need is therefore: 
“Synchronizing demand commitments with executable operational flow capacity.”

# 4. Vector Recommendations

The proposed product must be Dynamic Operational Synchronization & Scheduling Platform. It should convert Berau shipment demand into an executable ABL logistics plan by coordinating cargo readiness, jetty loading, tug-barge movement, tide and bridge windows, CTS availability, OGV loading sequence, exception recovery, approval and publication.

The platform should not only be a fleet-tracking screen, map view or digital Excel replacement. It should be a governed scheduling and simulation application designed to place each shipment movement through eligible route steps, available operating windows and approved decision workflows.

- Vector will use its proprietary scheduling, scenario and dynamic-constraint scaffolding as the base for the application build. The ABL-specific implementation will configure and extend this base around Berau demand, ABL assets, tide and bridge logic, port/CTS operations, recovery workflows, approval governance and required integrations.

# 5. Business Use Case

Operating principle: Synchronize Berau Coal's shipment commitments with ABL's real operational flow capacity so that cargo readiness, asset availability, tide/bridge windows, jetty/CTS capacity, OGV loading sequence and recovery decisions are planned and governed from one shared operating platform.

## 5.1 Business problems addressed

| Business problem | Application response |
| --- | --- |
| Static Excel planning cannot absorb daily and intra-day changes | Structured demand intake, versioned plan generation, conflict checks, approval and governed replanning |
| Shipment demand is not continuously synchronized with logistics capacity | OGV demand, cargo grade, route, tug-barge, jetty, CTS and operating-window capacity are held in one planning model |
| Tide, bridge and berth windows keep changing the feasible plan | Movement windows are treated as schedulable capacity |
| Coal grade and loading sequence affect execution | Cargo requirement and layer sequence are first-class planning inputs |
| Existing work in progress affects new planning | Active plans, sailing barges, loaded barges, queues and confirmed actuals are plotted before new planning decisions |
| Operating exceptions are currently handled through experience and manual coordination | Exception families, reason codes, manual override and recovery workflows are captured in the governed process |
| Asset position is visible but operational status may require confirmation | GPS/AIS evidence is separated from confirmed operational events and schedule authority |
| Approvals and operating decisions require traceability | Dual-party approvals, immutable published snapshots, audit events and governed exports |

# 6. Core Scheduling Philosophy

Operating principle: Each shipment movement is treated as a schedulable entity that must pass through a defined route of operational steps. Each step needs the right resource, enough available capacity and a valid operating window.

For ABL, the route is operational as well as physical:

Cargo readiness -> Jetty / BLC loading -> Tug-barge departure -> Tide / river movement -> Bridge crossing -> CTS / anchorage queue -> CTS discharge -> OGV hatch / layer completion -> Survey / handover closure

The controlling constraint shifts during the day between tide, bridge, jetty, CTS, berth, tug-barge availability, cargo readiness and OGV laycan pressure. The application will therefore recalculate feasibility around moving operating windows and current execution state, not only around static planned dates.

# 7. Vector Proprietary Scheduling And Scenario Scaffolding

Vector owns a proprietary base scaffolding for constraint-aware scheduling, scenario simulation and dynamic-capacity planning. This base will be used as the starting point for the ABL application build.

## 7.1 Capabilities provided by the base scaffolding

| Capability | Role in ABL build |
| --- | --- |
| Scheduling entity model | Represents shipment movements, route steps, dependencies, priorities and target dates |
| Route and resource eligibility | Matches each movement with allowed jetties, routes, tug-barge pairs, CTS assets and operating steps |
| Capacity-window placement | Places movements into free operating windows and prevents invalid overlap |
| Current-state loading | Considers active work, occupied resources, queues and confirmed actuals before placing new work |
| Dynamic constraint evaluation | Rechecks feasibility when tide, bridge, berth, asset or cargo readiness changes |
| Scenario engine | Simulates delay, outage, window-change, reassignment and recovery assumptions |
| Candidate comparison | Evaluates alternate paths and recovery options against feasibility and impact |
| Exception and blocker output | Identifies the first operating blocker and the affected downstream commitments |

## 7.2 ABL-specific configuration and extension

The ABL build will configure this base around:

- Berau OGV demand, cargo quantity, coal grade and layer sequence

- ABL jetties, BLC loading capability, tug-barge fleet and CTS assets

- tide windows, bridge windows, river movement and route cycle times

- cargo readiness, stockpile/source eligibility and quality-release status

- active trip state, loaded barges, queues and confirmed operational events

- exception categories, recovery rules, approvals and publishability gates

- reporting, dashboard, audit and export requirements.

The proprietary base accelerates implementation while the blueprinting phase ensures that ABL-specific business rules, data interfaces and governance logic are validated before full deployment.

# 8. Product Development Layers

## 8.1 Layer 1 - Governed scheduling model

This layer creates the structured planning spine:

- OGV voyage and laycan intake

- cargo quantity, coal grade and loading sequence

- source, stockpile, jetty and route master data

- tug, barge and CTS availability

- tide and bridge calendars

- deterministic schedule generation

- conflict detection

- manual override with reason capture

- plan versioning

- approval, publish and audit.

## 8.2 Layer 2 - Operating readiness and exception governance

This layer organizes how the scheduling model is adopted into day-to-day planning:

- planner workflow validation

- demand completeness and master-data readiness

- conflict reason review

- override pattern review

- exception family definition

- approval latency review

- readiness review before activating later operating layers.

## 8.3 Layer 3 - Simulation and operational evidence

This layer adds scenario and live-state interpretation:

- delay, outage, window-change and reassignment assumptions

- projected trip, event, OGV completion and utilization impact

- GPS/AIS-style position evidence

- geofence, ETA variance and stale-signal alerts

- event candidates from device, operator or feed input

- trusted confirmation before schedule actualization.

## 8.4 Layer 4 - Recovery and guided execution

This layer adds guided decision support:

- recovery input snapshots from active plan, alerts, confirmed events and conflicts

- ranked recovery options

- root-cause validation

- scenario creation from selected recovery option

- publishability assessment

- guided operator workflow

- projection-only commercial and operating-impact review surfaces.

# 9. Phase Of Development in Sprint Level

| Sprint level | Build focus | Key outcome |
| --- | --- | --- |
| Sprint 0 | Application foundation: web application, API service, database, background processing, file storage and routing layer | Runnable product spine |
| Sprint 1 | Master data and governance: organizations, roles, audit, locations, cargo, jetties, routes, assets and compatibility | Safe multi-party operating model |
| Sprint 2 | Demand and capacity intake: OGV demand, cargo layer, asset windows, jetty windows, tide windows and bridge windows | Structured inputs for planning |
| Sprint 3 | Scheduling entity and route model: trips, assignments, schedule events and route-step dependencies | Movement chain represented as schedulable work |
| Sprint 4 | Capacity placement and feasibility: candidate paths, occupied/free windows, conflict checks and movement candidates | Feasible plan with explicit blockers |
| Sprint 5 | Plan governance: versions, overrides, approval requests, approval decisions, published snapshots and exports | Approved execution contract |
| Sprint 6 | Scenario simulation and exception review: assumptions, projected events, projected trips, constraint evaluations, exception families and utilization outputs | What-if planning and exception impact visibility |
| Sprint 7 | Live evidence: telemetry sources, asset identities, position pings, latest asset state, geofences and ETA variance | Planned-vs-observed movement visibility |
| Sprint 8 | Confirmed operations: integration feeds, devices, event candidates, confirmed events, actualization and device health | Trusted execution status layer |
| Sprint 9 | Recovery recommendations: input snapshots, ranked options, recovery actions and proof pack | Decision support for disrupted flow |
| Sprint 10 | Guided recovery and hardening: workflow guidance, root-cause validation, publishability, review surfaces and tests | Pilot-ready governed flow-management platform |

The first release will prove the governed scheduling spine and operating-window logic. Later releases will progressively add simulation, live evidence, trusted field events, recovery guidance and management review surfaces.

## 9.1 Client delivery blocks

| Delivery block | Sprint coverage | System screens delivered | Capability delivered | Product owned by ABL at this stage |
| --- | --- | --- | --- | --- |
| Release 1 - Governed scheduling spine | Sprint 0 to Sprint 5 | Login and role-based navigation, master data, OGV demand, cargo layer sequence, tide/bridge windows, tug-barge assignment, jetty loading, CTS operations, conflict review, override reason capture, approval, published plan, audit and export screens | Structured demand intake, master-data setup, operating-window entry, route/resource eligibility, candidate movement generation, feasibility checks, conflict output, plan versioning, dual approval, manual publish and governed export | A working governed scheduling application that replaces spreadsheet-only planning for the core ABL-Berau flow and creates an approved execution contract |
| Release 2 - Exception and scenario support | Sprint 6 | Exception review, scenario assumption entry, baseline-versus-scenario comparison, projected trip/event impact, constraint impact and utilization review screens | Exception family handling, what-if planning for delay/outage/window change/reassignment, projected downstream impact and scenario promotion into approval path | A planning simulation and exception review product that allows ABL to test disruption impact before changing the published plan |
| Release 3 - Live evidence and confirmed operations | Sprint 7 to Sprint 8 | Live resource map, asset signal detail, tracking alert list, operations event console, device/feed health, jetty/CTS actualization and exception linkage screens | GPS/AIS-style evidence ingestion, latest asset state, geofence/ETA variance, stale-signal alerts, event candidate capture, event confirmation, actual execution update and trusted exception creation | An execution-monitoring layer that connects the approved schedule with observed and confirmed field reality |
| Release 4 - Recovery guidance and flow-management hardening | Sprint 9 to Sprint 10 | Recovery recommendation console, ranked option detail, root-cause validation, publishability review, guided workflow panel, management review surfaces and hardened audit evidence screens | Ranked recovery options, recovery proof pack, guided next action, publishability validation, telemetry-trust review and projection-only operating/commercial visibility | A governed flow-management platform that supports disruption recovery from exception identification to approved recovery publication |

# 10. Release 1 - Governed Scheduling Spine

Release 1 establishes the governed scheduling spine and operating-window logic across Sprint 0 to Sprint 5. It creates the first complete product layer that ABL can use for structured planning, feasibility review, approval and publication.

## 10.1 Release 1 system screens

| Screen group | Release 1 coverage |
| --- | --- |
| Access and governance | Login, role-based navigation, organization, user, role and approval authority screens |
| Master data | Locations, cargo grades, sources, stockpiles, jetties, routes, tug/barge/CTS assets and compatibility |
| Demand and cargo | OGV demand intake, laycan, cargo quantity, coal grade and cargo layer sequence |
| Operating windows | Asset availability, jetty/BLC windows, tide windows, bridge windows and CTS capacity windows |
| Scheduling | Candidate movement generation, tug-barge assignment, schedule events, conflict output and draft plan review |
| Approval and publish | Override capture, approval request, approval decision, publishability check, published snapshot and export |
| Audit and evidence | Plan history, approvals, manual overrides, exports and audit events |

## 10.2 Release 1 capability delivered

Release 1 delivers:

- structured demand intake

- master-data and resource setup

- cargo layer and loading sequence representation

- route and resource eligibility checks

- operating-window entry and validation

- candidate movement generation

- explicit conflict and blocker output

- reason-coded manual override

- plan versioning

- dual approval

- published plan snapshot

- governed export and audit trail.

## 10.3 Release 1 operating success measures

| Success measure | Validation direction |
| --- | --- |
| Publishable-plan cycle time | Time from demand intake to publishable plan becomes visible and measurable |
| Schedule rework | Repeated spreadsheet revisions and manual reconciliation are reduced |
| Conflict clarity | Hard blockers carry a reason code, affected movement and review action |
| Approval traceability | Published plans carry approval, version and audit lineage |
| Planner adoption | Named users can complete representative planning workflows with controlled override usage |
| Data readiness | Demand, master data and operating-window inputs meet agreed minimum completeness |

Specific numeric targets will be baselined with ABL and Berau during pilot use.

# 11. Operational Readiness And Adoption Review

The operational readiness review confirms that the governed scheduling spine is aligned with real planning behavior before subsequent product layers are activated.

The review will cover:

- planner usage across representative scheduling workflows

- demand completeness and master-data stability

- conflict accuracy and false-positive blockers

- manual override frequency and reason-code quality

- approval latency and escalation behavior

- readiness of operating-window inputs

- exception families that need formal workflow treatment

- data and integration gaps to be resolved before live evidence or recovery automation.

The output of this review becomes the operating baseline for scenario simulation, exception support, live evidence, confirmed operations and recovery guidance.

# 12. Exception Taxonomy And Operating Governance